## New Website Pages
Category | Topic | Completeness | Phase 1 | Type of feature | Old | Effort | Questions/Comments | Requirement
Student Facing | Home Page- Search Bar | 70% | Yes | Page | Homepage | Medium
| Career Journey Map | 70% | Yes | Page | NA | High
| Deep Profiling | 90% | Yes | Page | Student Profile | Small |  | Provide profile details
| Journey Payment Page | 90% | Yes | Page | Signup | Small
| Student Dashboard - Overview | 50% | Yes | Page | Overview | Medium
| Student Dashboard - My Journey | 50% | Yes | Page | NA | High
| Student Dashboard - Career Journey Report | 50% | Yes | Page | NA | High
| Student Dashboard - Course List Page | 50% | Yes | Page | NA | Medium |  | Provide 2 Courses per Service
| Student Dashboard - Resources Overview | 50% | Yes | Page | NA | Medium |  | Provide 2 Resources
| Student Dashboard - Resources Details | 50% | Yes | Page | NA | Medium |  | Provide Resource Detail template
| Student Dashboard - Notifications Page | 50% | Yes | Page | Notifications | High
| Student Dashboard - Career Asset | 0 | Yes / No | Page
| Service Status Page | 0 | No | Page | NA | Medium
| Course Detail Page | 0 | Yes | Page | Course Detail | Medium |  | Provide Course Details template
| Course Entollment Page | 0 | Yes | Page | Cart | Medium
| Course Payment Page | 90% | Yes | Page | Payment | Small
| Payment Integration | 0 | Yes | Integration | Payment Integration | High |  | Provide payment integration details
| Caontact Us | 0 | Yes | Page | Caontact Us | Small
| About Merrakii | 0 | Yes | Page | About Merrakii | Small |  | Provide About Content
| Terms & Conditions | 0 | Yes | Page | Terms & Conditions | Small |  | Provide page content
| Privacy Policy | 0 | Yes | Page | Privacy Policy | Small |  | Provide page content
| Refund Policy | 0 | Yes | Page | Refund Policy | Small |  | Provide page content
| FAQs | 0 | Yes | Page | FAQs | Small |  | Provide page content
Admin Panel | Career Library CMS Overview (Career= Profession + Course + College + Exam) |  | Yes | Page | Course Library Overview | Medium | This will give the overview of all the Careers existing in the system
| Add Career Page per category per stream |  | Yes | Page | Add Course | High | This will let Admin perform CRUD(Create, Read, Update, Delete) operations on each Career.
| User Management - Overview |  | Yes | Page | NA | Medium | Students accounts only
| User Management - Add Student |  | Yes | Page | NA | High
| Service Knowledge Page Overview |  | Yes | Page | NA | Small | This will give the overview of all the Services existing in the system
| Add Service Knowledge |  | Yes | Page | Na | Medium | This will let Admin perform CRUD(Create, Read, Update, Delete) operations on each Service.
| Exam Overview | [5 empty] | Discuss on Metadata
Exam Add
| College Overview | [5 empty] | Discuss on Metadata
College Add
| Courses Overview page |  | Yes | Page | Course Library Overview | Medium | This will give the overview of all the Courses existing in the system
| Add Courses per career per service |  | Yes | Page | Add Course | High | This will let Admin perform CRUD(Create, Read, Update, Delete) operations on each Course.
| Counsellor Overview |  | No | Page | NA | Medium | This will give the overview of all the Counsellor profiles in the system
| Add Counsellor |  | No | Page | NA | High | This will let Admin perform CRUD(Create, Read, Update, Delete) operations on each Counsellor profile.
| Resources Overview |  | Yes | Page | NA | Medium | This will give the overview of all the Resources in the system
| Add Resources |  | Yes | Page | NA | High | This will let Admin perform CRUD(Create, Read, Update, Delete) operations on each Resource.
| Financials overview |  | Yes | Page | NA | High | Showcase financial summary per student
| Add Financials |  | No | Page | NA | High | Add Financial Transactions not happening in the system like Partner Commission
Backend | Access & security |  | Yes | Backend | Access & security | High | Server-side controls that decide who can sign in, what each role can see, and how student and parent data stays protected across the platform.
| Search & personalisation |  | Yes | Backend | Search & personalisation | High | Backend logic that turns a student’s search or intake details into the right career journeys, filters, and personalised pathway recommendations.
| Integrations |  | Yes | Backend | Integrations | High | Connections to external systems like Razorpay, email, linkedin, instagram, and whatsapp, including webhooks, credentials, and sync handling.
| Responsiveness |  | Yes | Backend | Responsiveness | High | Ensures the UI layout, navigation, and content adapt cleanly across screen sizes — from mobile phones to desktop — so every page remains usable without a separate app or design.
| Data & architecture |  | Yes | Backend | Data & architecture | High | The database design, API structure, and shared data models that hold journeys, services, users, and decisions together reliably as the product grows.
| Business logic / workflows |  | Yes | Backend | Business logic / workflows | High | The rules engines behind enrolment tiers, service status, counsellor sessions, decision logging, payments, and journey validation — not the screens that display them.
| DevOps & reliability |  | Yes | Backend | DevOps & reliability | High | How the app is deployed, monitored, and kept running on AWS — staging/production setup, CI/CD, health checks, backups, and uptime targets.
| Compliance & quality (non-UI) |  | Yes | Backend | Compliance & quality (non-UI) | High | Validation, audit trails, error handling, and security standards that keep the platform safe and trustworthy without changing what users see on screen.

## Previous Website Pages
Page category | Page route | Purpose
Marketing / entry | /homepage | Main landing page for Study Abroad and Study in India.
Discovery / catalogue | /catalog | Browse the full catalogue of programmes from contracted institutes.
Discovery / catalogue | /institutes/[id] | Institute profile with programmes, details, and enrolment options.
Discovery / catalogue | /course | Course/programme detail page for enrolment decisions.
Application / payment | /apply/[programId] | Structured application form for a selected programme.
Application / payment | /cart | Hold selected courses before checkout/enrolment.
Application / payment | /payment/[applicationId] | Pay for a specific application (including UPI/payment options).
Application / payment | /payment/checkout | Final checkout step to complete fee payment.
Application / payment | /payment/success | Confirmation screen after successful payment/enrolment.
Student account / auth | /login | Student/guardian sign-in (phone OTP).
Student account / auth | /account | Personal account to view applications and enrolment status.
Contact Us | /contactus | Contact Us
Staff admin | /dashboard | Staff console home for catalogue and operations.
Staff admin | /dashboard/login | Admin sign-in to manage institutes, courses, and catalogue.
Staff admin | /dashboard/homepage | Admin control for homepage/content configuration.
Staff admin | /dashboard/addvendor | Add a new contracted vendor/institute to the catalogue.
Staff admin | /dashboard/editvendor | Edit an existing vendor/institute record.
Staff admin | /dashboard/courses | Manage the list of programmes/courses in the catalogue.
Staff admin | /dashboard/course-detail | Create or edit a single course’s catalogue details.