## New Website Pages
Category | Topic | Phase 1 | Type of feature | Old | Effort | Questions/Comments | Requirement
Student Facing | Home Page- Search Bar | Yes | Page | Homepage | Medium
| Career Library - Level 1 Streams | Yes | Page | Course Library | Medium | Does Student gets to see this page? If yes, after payment of 99 or before that? Are there two ways to create journey: Homepage -> Search for a Career -> Land on Journey Map page Carrer Library -> Navigate to a stream -> Navigate to a career -> Map -> Land on Journey Map page | Provide 2 Career streams
| Career Library - Level 2 Career Category list per stream | Yes | Page | NA | Medium |  | Provide 3 Career Categories
| Career Detail - Per Career | Yes | Page | NA | High |  | Provide 4 Career Details
| Career Journey Map | Yes | Page | NA | High
| Deep Profiling | Yes | Page | Student Profile | Small |  | Provide profile details
| Signup ₹99 | Yes | Page | Signup | Small
| Career Journey Report | Yes | Page | NA | High | This will move inside Student Dashboard. The flow: Search -> Career Journey -> Career Journey Report is looking smooth the first time. To navigate to Career Journey Report the second time, it has to be in the dashboard.
| Service Knowledge Page | No | Page | NA | Medium |  | Provide 4 Services per career
| Course List Page | Yes | Page | NA | Medium |  | Provide 2 Courses per Service
| Service Status Page | No | Page | NA | Medium
| Course Detail Page | Yes | Page | Course Detail | Medium |  | Provide Course Details template
| Course Entollment Page | Yes | Page | Cart | Medium
| Payment Page | Yes | Page | Payment | Small
| Payment Integration | Yes | Integration | Payment Integration | High |  | Provide payment integration details
| Student Dashboard - Overview | Yes | Page | Overview | Medium
| Student Dashboard - My Journey | Yes | Page | NA | High
| Student Dashboard - My Portfolio overview | No | Page | NA | High
| Student Dashboard - Public Portfolio | No | Page | NA | High |  | Provide Portfolio template
| Student Dashboard - Linkedin outbound integration | No | Integration | NA | High
| Student Dashboard - whatsapp outbound integration | No | Integration | NA | High
| Student Dashboard - PDF outbound integration | No | Integration | NA | High
| Student Dashboard - Instagram inbound integration | No | Integration | NA | High
| Student Dashboard - Twitter inbound integration | No | Integration | NA | High
| Student Dashboard - youtube inbound integration | No | Integration | NA | High
| Student Dashboard - linkedin inbound integration | No | Integration | NA | High
| Student Dashboard - Programmes | No | Page | Courses Enrolled | Small |  | Provide 2 Programmes
| Student Dashboard - My Counsellor Overview | No | Page | NA | Medium |  | Provide 2 Counsellor profile details
| Student Dashboard - Book a Session | No | Page | NA | Medium
| Student Dashboard - Session Page | No | Page | NA | Medium
| Student Dashboard - Message box | No | Page | NA | Medium
| Student Dashboard - Resources Overview | Yes | Page | NA | Medium |  | Provide 2 Resources
| Student Dashboard - Resources Details | Yes | Page | NA | Medium |  | Provide Resource Detail template
| Student Dashboard - Notifications Page | Yes | Page | Notifications | High
| Caontact Us | Yes | Page | Caontact Us | Small
| About Merrakii | Yes | Page | About Merrakii | Small |  | Provide About Content
| For Parents | Yes | Page | NA | Small |  | Provide page content
| Terms & Conditions | Yes | Page | Terms & Conditions | Small |  | Provide page content
| Privacy Policy | Yes | Page | Privacy Policy | Small |  | Provide page content
| Refund Policy | Yes | Page | Refund Policy | Small |  | Provide page content
| FAQs | Yes | Page | FAQs | Small |  | Provide page content
Admin Panel | Career Library CMS Overview | Yes | Page | Course Library Overview | Medium | This will give the overview of all the Careers existing in the system
| Add Career Page per category per stream | Yes | Page | Add Course | High | This will let Admin perform CRUD(Create, Read, Update, Delete) operations on each Career.
| User Management - Overview | Yes | Page | NA | Medium | Students accounts only
| User Management - Add Student | Yes | Page | NA | High
| Service Knowledge Page Overview | Yes | Page | NA | Small | This will give the overview of all the Services existing in the system
| Add Service Knowledge | Yes | Page | Na | Medium | This will let Admin perform CRUD(Create, Read, Update, Delete) operations on each Service.
| Courses Overview page | Yes | Page | Course Library Overview | Medium | This will give the overview of all the Courses existing in the system
| Add Courses per career per service | Yes | Page | Add Course | High | This will let Admin perform CRUD(Create, Read, Update, Delete) operations on each Course.
| Counsellor Overview | No | Page | NA | Medium | This will give the overview of all the Counsellor profiles in the system
| Add Counsellor | No | Page | NA | High | This will let Admin perform CRUD(Create, Read, Update, Delete) operations on each Counsellor profile.
| Resources Overview | Yes | Page | NA | Medium | This will give the overview of all the Resources in the system
| Add Resources | Yes | Page | NA | High | This will let Admin perform CRUD(Create, Read, Update, Delete) operations on each Resource.
| Approvals overview | No | Page | NA | High | Overview all pending approval requests
| Approve individual entry | No | Page | NA | High | Page to view entire content in detail to approve.
| Financials overview | Yes | Page | NA | High | Showcase financial summary per student
| Add Financials | No | Page | NA | High | Add Financial Transactions not happening in the system like Partner Commission
Backend | Access & security | Yes | Backend | Access & security | High | Server-side controls that decide who can sign in, what each role can see, and how student and parent data stays protected across the platform.
| Search & personalisation | Yes | Backend | Search & personalisation | High | Backend logic that turns a student’s search or intake details into the right career journeys, filters, and personalised pathway recommendations.
| Integrations | Yes | Backend | Integrations | High | Connections to external systems like Razorpay, email, linkedin, instagram, and whatsapp, including webhooks, credentials, and sync handling.
| Responsiveness | Yes | Backend | Responsiveness | High | Ensures the UI layout, navigation, and content adapt cleanly across screen sizes — from mobile phones to desktop — so every page remains usable without a separate app or design.
| Data & architecture | Yes | Backend | Data & architecture | High | The database design, API structure, and shared data models that hold journeys, services, users, and decisions together reliably as the product grows.
| Business logic / workflows | Yes | Backend | Business logic / workflows | High | The rules engines behind enrolment tiers, service status, counsellor sessions, decision logging, payments, and journey validation — not the screens that display them.
| DevOps & reliability | Yes | Backend | DevOps & reliability | High | How the app is deployed, monitored, and kept running on AWS — staging/production setup, CI/CD, health checks, backups, and uptime targets.
| Compliance & quality (non-UI) | Yes | Backend | Compliance & quality (non-UI) | High | Validation, audit trails, error handling, and security standards that keep the platform safe and trustworthy without changing what users see on screen.

## Previous Website Pages
Page category | Page route | Purpose
Marketing / entry | /homepage | Main landing page for Study Abroad and Study in India.
Discovery / catalogue | /catalog | Browse the full catalogue of programmes from contracted institutes.
Discovery / catalogue | /institutes/[id] | Institute profile with programmes, details, and enrolment options.
Discovery / catalogue | /course | Course/programme detail page for enrolment decisions.
Application / payment | /apply/[programId] | Structured application form for a selected programme.
Application / payment | /cart | Hold selected courses before checkout/enrolment.
Application / payment | /payment/[applicationId] | Pay for a specific application (including UPI/payment options).
Application / payment | /payment/checkout | Final checkout step to complete fee payment.
Application / payment | /payment/success | Confirmation screen after successful payment/enrolment.
Student account / auth | /login | Student/guardian sign-in (phone OTP).
Student account / auth | /account | Personal account to view applications and enrolment status.
Contact Us | /contactus | Contact Us
Staff admin | /dashboard | Staff console home for catalogue and operations.
Staff admin | /dashboard/login | Admin sign-in to manage institutes, courses, and catalogue.
Staff admin | /dashboard/homepage | Admin control for homepage/content configuration.
Staff admin | /dashboard/addvendor | Add a new contracted vendor/institute to the catalogue.
Staff admin | /dashboard/editvendor | Edit an existing vendor/institute record.
Staff admin | /dashboard/courses | Manage the list of programmes/courses in the catalogue.
Staff admin | /dashboard/course-detail | Create or edit a single course’s catalogue details.